## Standard Proposal
Sponsor deadline | 2023-07-05
Today's date | 2023-04-17
Proposal Stages | Deadline | Workdays remaining | Explanation of Deadline | Info for PI
Intent to Submit - REQUIRED FOA/RFP, prelim. demographics & initial budget info | 2023-05-19 | 25 | 30 business days before sponsor deadline | GCA to work with PI to produce timeline and due dates
PI/DOMRA - Working Period | N/A | 40 | 16-30 Business Days before sponsor deadline | Ongoing collaboration between DOMRA and PI during this time
DOMRA - Final documents to GCA submit-ready, all components in their final form | 2023-06-12 | 40 | 15 business days preceding sponsor deadline - final documents encompassing all feedback | No further changes to anything, including attachments
Institutional Review submit-ready, all components in their final form | 2023-06-20 | 44 | 10 business days before the sponsor deadline - proposal routes in SPS for departmental and ORA review | These are DOMRA/ORA deadlines; PI should be available and responsive to questions/requested changes
ORA (by 8am) submit-ready proposal, all permissions granted | 2023-06-27 | 49 | 8am 5 business days before the sponsor deadline
Sponsor submit-ready proposal with all approvals completed | 2023-07-05 | 55 | as published in the opportunity announcement or by the prime awardee institution (if Duke is a sub)
Formulas:
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline],Holidays),0)
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline, row below],Holidays),0)

## Sheet1 (hidden)
Days prior | # of days with it | Step
30 |  | PI sends intent to submit
| 15 | Work work work, iteration iteration iteration
15 |  | PI returns all docs and budget with GCA changes incorporated
| 5 | GCA puts everything where it goes and submits to departmental approvers
10 | 5 | Departmental review
5 | 5 | ORA Review

## Proposals With Subawards
Sponsor deadline | 2023-06-05
Today's date | 2023-04-17
Proposal Stages | Deadline | Workdays remaining | Explanation of Deadline | Info for PI
Intent to Submit - REQUIRED FOA/RFP, prelim. demographics & initial budget info | 2023-03-10 | 0 | 60 business days before sponsor deadline | GCA to work with PI to produce timeline and due dates
DOMRA - Subaward Docs *full, institutionally-approved subaward packet | 2023-05-05 | 15 | 20 business days preceding sponsor deadline | GCA to communicate this deadline to subs as early as possible
PI/DOMRA - Working Period | N/A | 20 | 16-60 Business Days before sponsor deadline | Ongoing collaboration between DOMRA and PI during this time
DOMRA - Final documents to GCA submit-ready, all components in their final form | 2023-05-12 | 20 | 15 business days preceding sponsor deadline - final documents encompassing all feedback | No further changes to anything, including attachments
Institutional Review submit-ready, all components in their final form | 2023-05-19 | 24 | 10 business days before the sponsor deadline - proposal routes in SPS for departmental and ORA review | These are DOMRA/ORA deadlines; PI should be available and responsive to questions/requested changes
ORA (by 8am) submit-ready proposal, all permissions granted | 2023-05-26 | 29 | 8am 5 business days before the sponsor deadline
Sponsor submit-ready proposal with all approvals completed | 2023-06-05 | 35 | as published in the opportunity announcement or by the prime awardee institution (if Duke is a sub)
*subject to change depending on complexity of proposal
Formulas:
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline],Holidays),0)
Workdays remaining = NETWORKDAYS(B2,[Deadline],Holidays)

## Data (hidden)
HOLIDAYS
2022-06-20
2022-07-04
2022-09-05
2022-11-24
2022-12-26
2023-01-02
2023-01-16
2023-05-29
2023-06-19
2023-07-04
2023-09-04
2023-11-23
2023-12-25
2024-01-01