## Standard Proposal
Sponsor deadline | 2025-03-11
Today's date | 2024-12-17
Proposal Stages | Deadline | Workdays remaining | Explanation of Deadline | Info for PI
Intent to Submit - REQUIRED FOA/RFP, prelim. demographics & initial budget info | 2025-01-28 | 28 | 30 business days before sponsor deadline | Rule of thumb: as soon as you know, start working with your GCA
PI/DOMRA - Working Period required documents in draft form for GCA feedback | N/A | 43 | 16-30 Business Days before sponsor deadline | Exchanging draft iterations of budget, justification, biosketches, etc.
DOMRA - Final documents to GCA submit-ready, all components in their final form | 2025-02-18 | 43 | 15 business days preceeding sponsor deadline - final documents encompassing all feedback | Pencils down - no further changes to anything, including attachments
Institutional Review submit-ready, all components in their final form | 2025-02-25 | 47 | 10 business days before the sponsor deadline - proposal routes in SPS for departmental and ORA review | These are DOMRA/ORA deadlines; PI should be available and responsive to questions/requested changes
ORA (by 8am) submit-ready proposal, all permissions granted | 2025-03-04 | 52 | 8am 5 business days before the sponsor deadline
Sponsor submit-ready proposal with all approvals completed | 2025-03-11 | 58 | as published in the opportunity announcement or by the prime awardee institution (if Duke is a sub)
Formulas:
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline],Holidays),0)
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline, row below],Holidays),0)

## Sheet1 (hidden)
Days prior | # of days with it | Step
30 |  | PI sends intent to submit
| 15 | Work work work, iteration iteration iteration
15 |  | PI returns all docs and budget with GCA changes incorporated
| 5 | GCA puts everything where it goes and submits to departmental approvers
10 | 5 | Departmental review
5 | 5 | ORA Review

## Large Proposals-with Subs
Sponsor deadline | 2025-02-05
Today's date | 2024-12-17
Proposal Stages | Deadline | Workdays remaining | Explanation of Deadline | Info for PI
Intent to Submit - REQUIRED FOA/RFP, prelim. demographics & initial budget info | 2024-11-07 | 0 | 60 business days before sponsor deadline | Rule of thumb: as soon as you know, start working with your GCA
DOMRA - Subaward Docs *full, institutionally-approved subaward packet | 2025-01-07 | 14 | 20 business days preceeding sponsor deadline | GCA to communicate this deadline to subs as early as possible
PI/DOMRA - Working Period required documents in draft form for GCA feedback | N/A | 19 | 16-60 Business Days before sponsor deadline | Exchanging draft iterations of budget, justification, biosketches, etc.
DOMRA - Final documents to GCA submit-ready, all components in their final form | 2025-01-14 | 19 | 15 business days preceeding sponsor deadline - final documents encompassing all feedback | Pencils down - no further changes to anything, including attachments
Institutional Review submit-ready, all components in their final form | 2025-01-22 | 23 | 10 business days before the sponsor deadline - proposal routes in SPS for departmental and ORA review | These are DOMRA/ORA deadlines; PI should be available and responsive to questions/requested changes
ORA (by 8am) submit-ready proposal, all permissions granted | 2025-01-29 | 28 | 8am 5 business days before the sponsor deadline
Sponsor submit-ready proposal with all approvals completed | 2025-02-05 | 34 | as published in the opportunity announcement or by the prime awardee institution (if Duke is a sub)
*subject to change depending on complexity of proposal
Formulas:
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline],Holidays),0)
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline, row below],Holidays),0)

## Large Proposals-Other
Sponsor deadline | 2024-10-07
Today's date | 2024-12-17
Proposal Stages | Deadline | Workdays remaining | Explanation of Deadline | Info for PI
Intent to Submit - REQUIRED FOA/RFP, prelim. demographics & initial budget info | 2024-07-12 | 0 | 60 business days before sponsor deadline | Rule of thumb: as soon as you know, start working with your GCA
PI/DOMRA - Working Period required documents in draft form for GCA feedback | N/A | 0 | 16-60 Business Days before sponsor deadline | Exchanging draft iterations of budget, justification, biosketches, etc.
DOMRA - Final documents to GCA submit-ready, all components in their final form | 2024-09-16 | 0 | 15 business days preceeding sponsor deadline - final documents encompassing all feedback | Pencils down - no further changes to anything, including attachments
Institutional Review submit-ready, all components in their final form | 2024-09-23 | 0 | 10 business days before the sponsor deadline - proposal routes in SPS for departmental and ORA review | These are DOMRA/ORA deadlines; PI should be available and responsive to questions/requested changes
ORA (by 8am) submit-ready proposal, all permissions granted | 2024-09-30 | 0 | 8am 5 business days before the sponsor deadline
Sponsor submit-ready proposal with all approvals completed | 2024-10-07 | 0 | as published in the opportunity announcement or by the prime awardee institution (if Duke is a sub)
Formulas:
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline],Holidays),0)
Workdays remaining = MAX(NETWORKDAYS(B2,[Deadline, row below],Holidays),0)

## Complex Proposals
Intent to Submit - REQUIRED FOA/RFP, prelim. demographics & initial budget info | 4-6 MONTHS PRIOR TO SPONSOR DEADLINE - FURTHER DEADLINES WILL BE SET ON CASE-BY-CASE BASIS

## Data (hidden)
HOLIDAYS
2024-09-02
2024-11-28
2024-12-25
2025-01-01
2025-01-20
2025-05-26
2025-06-19
2025-07-04
2025-09-01
2025-11-27
2025-12-25
2026-01-01
2026-01-19
2026-05-25
2026-07-03
2026-09-07
2026-11-26
2026-12-25
2027-01-01
2027-01-18
2027-05-31
2027-07-05
2027-09-06
2027-11-25
2027-12-25
2028-01-01